## GanttChart
Econforecasting
| Project Start Date | 2020-12-27 |  |  |  |  | Display Week | 58 |  | Week 58 | [6 empty] | Week 59 | [6 empty] | Week 60 | [6 empty] | Week 61 | [6 empty] | Week 62 | [6 empty] | Week 63 | [6 empty] | Week 64 | [6 empty] | Week 65
| Project Lead | C$ | [7 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21
 | time axis 2022-01-31 to 2022-03-27
WBS | TASK |  | PREDECESSOR | TECH | START | END | DAYS | % DONE | WORK DAYS | time axis 2022-01-31 to 2022-03-27
1 | Initial Setup |  |  |  |  | - |  |  | -
1.1 | Buy Domain |  |  | NA | 2020-12-27 | 2020-12-28 | 5 | 100% | 1
1.2 | Update Existing Server |  |  | Bash | 2020-12-27 | 2020-12-30 | 5 | 100% | 3
1.3 | Nginx Setup |  |  | Bash | 1930-12-27 | 2020-12-30 | 4 | 100% | 3
1.4 | PHP Update |  |  | PHP | 1930-12-27 | 2020-12-30 | 4 | 100% | 23483
1.5 | Favicon/Logo Design |  |  | NA | 1930-12-27 | 2021-01-10 | 5 | 100% | 23490
1.6 | Bootstrap/Front-end Setup |  |  | CSS | 2020-12-27 | 2020-12-31 | 7 | 100% | 4
1.7 | CMEFI Email Setup |  |  | NA | 2021-01-05 | 2021-01-05 | 7 | 100% | 1
1.8 | Git Setup |  |  | NA | 2021-01-05 | 2021-01-10 | 5 | 100%
2 | Initial Data Agg & Setup |  |  |  |  | - |  |  | -
2.1 | R Package Initiation |  |  | R | 2020-12-31 | 2021-01-10 | 4 | 100% | 7
2.2 | Scrape GDPNow |  |  | R | 2021-01-05 | 2021-01-05 | 3 | 100% | 1
2.3 | Scrape Phildelphia Fed |  |  | R | 2021-01-05 | 2021-01-05 | 3 | 100% | 1
2.4 | Scrape WSJ |  |  | R | 2021-01-06 | 2021-01-07 | 6 | 100% | 2
2.5 | Scrape CBO |  |  | R | 2021-01-07 | 2021-01-07 | 3 | 100% | 1
3 | Asset Contagion Migration |  |  |  |  | - |  |  | -
3.1 | PostgreSQL Setup |  |  | SQL | 2021-01-07 | 2021-01-10 | 4 | 100% | 2
3.2 | Scrape Yahoo Finance |  |  | R | 2021-01-08 | 2021-01-08 | 3 | 100% | 1
3.3 | Import Old SQL Fund Info |  |  | SQL | 2021-01-09 | 2021-01-09 | 3 | 100% | 0
3.4 | SQL INSERT Code |  |  | SQL | 2021-01-09 | 2021-01-10 | 4 | 100%
3.5 | Setup JS Code for Data |  |  | JS | 2021-01-10 | 2021-01-10 | 6 | 100% | 0
3.6 | Setup JS Code for Heatmap |  |  | JS | 2021-01-10 | 2021-01-14 | 3 | 100% | 4
3.7 | Improve Heatmap Appearance |  |  | JS | 2021-01-25 | 2021-01-27 | 4 | 100%
3.8 | Add ts chart |  |  | JS | 2021-01-25 | 2021-01-27 | 5 | 100%
3.9 | Add description |  |  | HTML | 2021-01-25 | 2021-01-29 | 5 | 100%
3.10 | Bootstrap 5 Upgrade |  |  | CSS | 2021-01-25 | 2021-01-28 | 5 | 100%
3.11 | GA Tracking |  |  | NA | 2021-01-28 | 2021-01-28 | 6 | 100%
3.12 | Add Datatables |  |  | JS | 2021-01-27 | 2021-01-29 | 7 | 100%
3.13 | Add CSV Export |  |  | JS | 2021-01-27 | 2021-01-29 | 8 | 100%
3.14 | Add Temp Logo |  |  | CSS | 2021-01-29 | 2021-01-29 | 9 | 100%
4 | Forecasts & Live Website |  |  |  |  | - |  |  | -
4.1 | Fed Funds Forecasts |  |  | R | 2021-01-27 | 2021-01-27 | 1 | 100% | 1
4.2 | DNS Forecast Decomp |  |  | R | 2021-01-30 | 2021-01-30 | 1 | 100% | 0
4.3 | Scrape Third Party Sites |  |  | R | 2021-02-03 | 2021-02-03 | 1 | 100% | 1
4.4 | SEO Setup (Robots + Sitemap) |  |  | XML | 2021-02-03 | 2021-02-04 | 1 | 100% | 2
4.5 | Setup AJAX Requests |  |  | PHP | 2021-02-03 | 2021-02-03 | 1 | 100% | 1
4.6 | Create Tyield Charts |  |  | JS | 2021-02-03 | 2021-02-05 | 1 | 100%
4.7 | Create Tyield Datatables |  |  | JS | 2021-02-03 | 2021-02-05 | 1 | 100%
4.8 | Create Tyield Docs |  |  | HTML | 2021-02-03 | 2021-02-05 | 1 | 100%
4.9 | Create Full Tyield Curve |  |  | JS | 2021-02-04 | 2021-02-06 |  | 100%
4.10 | LastVintagesByVarname SQL |  |  | SQL | 2021-02-09 | 2021-02-10 |  | 100%
4.11 | FFR Forecast Chart |  |  | JS | 2021-02-09 | 2021-02-09 |  | 100%
4.12 | SOFR Forecast Scraping |  |  | R | 2021-02-09 | 2021-02-10 |  | 100%
4.13 | SASS/SCSS Setup |  |  | CSS | 2021-02-09 | 2021-02-09 |  | 100%
4.14 | Palette & Theming |  |  | CSS | 2021-02-09 | 2021-02-10 |  | 100%
4.15 | Homepage Styling |  |  | HTML | 2021-02-10 | 2021-02-10 |  | 100%
4.16 | Update AJAX to Fetch Requests |  |  | JS | 2021-02-09 | 2021-02-11 |  | 100%
4.17 | FFR Datatables |  |  | JS | 2021-02-10 | 2021-02-11 |  | 100%
4.18 | FFR Model Description |  |  | HTML | 2021-02-11 | 2021-02-11 |  | 100%
4.19 | Fix Gutter Bug |  |  | CSS | 2021-02-11 | 2021-02-11 |  | 100%
4.20 | SOFR Forecast Chart |  |  | JS | 2021-02-11 | 2021-02-11 |  | 100%
4.21 | SOFR Datatables |  |  | JS | 2021-02-11 | 2021-02-12 |  | 100%
4.22 | SOFR Model Description |  |  | HTML | 2021-02-11 | 2021-02-12 |  | 100%
4.23 | Mortgage Model |  |  | R | 2021-02-12 | 2021-02-12 |  | 100%
4.24 | Mortgage Datatables & Chart |  |  | JS | 2021-02-12 | 2021-02-13 |  | 100%
5 | Forecast Improvements & Monthly Data Models |  |  |  |  | - |  |  | -
5.1 | Fix SOFR & FFR CME Bug |  |  | R | 2021-02-15 | 2021-02-15 | 1 | 100% | 1
5.2 | Add HC Theme Consistency |  |  | JS | 2021-02-16 | 2021-02-16 | 1 | 100% | 1
5.3 | Add Monthly Interpolation |  |  | JS | 2021-02-17 | 2021-02-17 | 1 | 100% | 1
5.4 | Added Table for Last Vintages Only |  |  | SQL | 2021-02-17 | 2021-02-17 | 1 | 100% | 1
5.5 | SEM Seasonalization |  |  | R | 2021-02-15 | 2021-02-17 | 1 | 100%
5.6 | Setup SEM Basics |  |  | R | 2021-02-17 | 2021-02-17 |  | 100%
5.7 | Kalman Smoothing |  |  | R | 2021-02-17 | 2021-02-17 |  | 100%
5.8 | Expected Inflation Model |  |  | R | 2021-02-17 | 2021-02-17 |  | 100%
5.9 | Added Expected Inflation to EF |  |  | JS | 2021-02-17 | 2021-02-17 |  | 100%
5.10 | Expected Inflation Description |  |  | HTML | 2021-02-18 | 2021-02-18 |  | 100%
6 | Add KF Nowcasts & Blog |  |  |  |  | - |  |  | -
6.1 | Add Full GDP Subcomponent import |  |  | R | 2021-02-20 | 2021-02-20 | 1 | 100% | 0
6.2 | Add Blog Structure |  |  | CSS | 2021-02-20 | 2021-02-21 |  | 100%
6.3 | Add First Blog Component |  |  | HTML | 2021-02-21 | 2021-02-21 |  | 100%
6.4 | Add Dynamic Factor Models |  |  | R | 2021-02-22 | 2021-02-22 |  | 100%
6.5 | Add Kalman Filter & Smoother |  |  | R | 2021-02-22 | 2021-02-23 |  | 100%
6.6 | Add Kalman Documentation |  |  | Latex | 2021-02-22 | 2021-03-04 |  | 100%
6.7 | Add NC SQL Database |  |  | SQL | 2021-03-05 | 2021-03-05 |  | 100%
6.8 | Add NC to Website |  |  | JS | 2021-03-05 | 2021-03-12 |  | 100%
6.9 | Improve Nowcasts - Elastic Net Regularization |  |  | R | 2021-03-12 | 2021-03-16 |  | 100%
6.10 | Add Elastic Net Documentation |  |  | R | 2021-03-19 | 2021-03-19 |  | 100%
7 | Toy Structural Model & Improve Nowcasts |  |  |  |  | - |  |  | -
7.1 | Begin Theory for Structural Framework |  |  | R | 2021-03-19 | 2021-03-22 |  | 100% | 2
8 | Improve Forecasts & Fix Bugs |  |  |  |  | - |  |  | -
8.1 | Update JS Dependencies |  |  | JS | 2021-05-07 | 2021-05-08 |  | 100% | 1
8.2 | Improve Nowcast Quality |  |  | R | 2021-05-08 | 2021-05-08 |  | 100%
8.3 | Scrape & Store Nowcast Releases |  |  | SQL | 2021-05-08 | 2021-05-08 |  | 100%
8.4 | Add Cleanup Code |  |  | R | 2021-05-08 | 2021-05-08 |  | 100%
8.5 | Add Nowcast Releases to UI |  |  | JS | 2021-05-08 | 2021-05-08 |  | 100%
8.6 | Add Data Release Onhover to Create Line on Highcharts |  |  | JS | 2021-05-10 | 2021-05-11 |  | 100%
8.7 | Fix Treasury Yield Forecasts |  |  | R | 2021-05-25 | 2021-05-25 |  | 100%
8.8 | Fix Asset Contagion |  |  | R | 2021-05-25 | 2021-05-25 |  | 100%
8.9 | Improve Inflation Forecasts |  |  | R | 2021-05-25 | 2021-05-25 |  | 100%
9 | Structural Model Dev |  |  |  |  | - |  |  | -
9.1 | Revise Data Imports |  |  | R | 2021-05-26 | 2021-05-31 |  | 100%
9.2 | Revise Data Transforms |  |  | R | 2021-05-30 | 2021-05-31 |  | 100%
9.3 | Add Baseline Qualitative-Adjustable Forecasts |  |  | R | 2021-06-07 | 2021-06-09 |  | 100%
9.4 | Add Separation of Initial/External Forecasts |  |  | R | 2021-06-09 | 2021-06-18 |  | 100%
9.5 | Add Initial Forecast Qual Derivaiton |  |  | R | 2021-06-18 | 2021-06-25 |  | 100%
9.6 | Add Other Initial Forecasts |  |  | R | 2021-06-28 | 2021-06-28 |  | 100%
10 | Model Rewrite P1-P3 |  |  |  |  | - |  |  | -
10.1 | Add Structural Estimation Dev |  |  | R | 2021-07-01 | 2021-07-05 |  | 100%
10.2 | Add Structural Forecasting Dev |  |  | R | 2021-07-01 | 2021-07-05 |  | 100%
10.3 | Update Model Flow |  |  | R | 2021-07-06 | 2021-07-06 |  | 100%
10.4 | Fix Nowcast Variables to Match New Tab |  |  | Excel | 2021-07-06 | 2021-07-07 |  | 100%
10.5 | Add Nowcast to New Flow |  |  | R | 2021-07-06 | 2021-07-13 |  | 100%
10.6 | Add Alt Initial Forecasts |  |  | R | 2021-07-13 | 2021-07-21 |  | 100%
11 | Model Creation P4 - CSM & Website Prep (v0.16) |  |  |  |  | - |  |  | -
11.1 | CSM Forecast Dates |  |  | R | 2021-07-21 | 2021-07-28 |  | 100%
11.2 | CSM Forecasting |  |  | R | 2021-07-28 | 2021-08-01 |  | 100%
11.3 | Nowcast Model Stacking - Reduce Variance |  |  | R | 2021-07-29 | 2021-08-01 |  | 100%
11.4 | CSM Transformations |  |  | R | 2021-08-02 | 2021-08-11 |  | 100%
11.5 | CSM Qualitative Forecast Refactoring & Forecasting |  |  | R | 2021-08-12 | 2021-08-16 |  | 100%
11.6 | CSM Equation Fixing (Moving Averages Bug) |  |  | R | 2021-08-16 | 2021-08-19 |  | 100%
11.7 | Add Proper Forecast Type Checks |  |  | R | 2021-08-21 | 2021-08-22 |  | 100%
11.8 | CSM Equation Validation |  |  | R | 2021-08-27 | 2021-08-30 |  | 100%
11.9 | Add Additional Scenarios |  |  | R | 2021-08-28 | 2021-08-30 |  | 100%
11.10 | Model Stacking CSM - Nowcasts |  |  | R | 2021-08-28 | 2021-08-30 |  | 100%
11.11 | Add Forecasts to SQL |  |  | SQL | 2021-08-29 | 2021-09-03 |  | 100%
12 | Model Prod (v0.17) |  |  |  |  | - |  |  | -
12.1 | Add Automation |  |  | R | 2021-09-04 | 2021-09-07 |  | 100%
12.2 | Add PHP Scenarios Pull |  |  | PHP | 2021-09-04 | 2021-09-05 |  | 100%
12.3 | Add Central Forecasts Page |  |  | JS | 2021-09-04 | 2021-09-22 |  | 100%
12.4 | Add Central Forecast Page Styling |  |  | CSS | 2021-09-08 | 2021-09-22 |  | 100%
12.5 | Model Data Resiliency Upgrades |  |  | R | 2021-10-06 | 2021-10-18 |  | 100%
12.6 | Split External Forecasts Import - Create Own Database |  |  | R | 2021-10-10 | 2021-10-18 |  | 100%
12.7 | Split Data Import |  |  | R | 2021-10-07 | 2021-10-19 |  | 100%
12.8 | Move Task Scheduler to Cron Job on Prod VPS |  |  | Bash | 2021-10-20 | 2021-10-21 |  | 100%
13 | Overhaul Prep (v0.18) |  |  |  |  | - |  |  | -
13.1 | Clean Folder, Improve Devops Flow |  |  | Bash | 2021-11-17 | 2021-11-18 |  | 100%
13.2 | Migrate to TimeScaleDB |  |  | SQL | 2021-11-23 | 2021-11-23 |  | 100%
13.3 | Restructure Database |  |  | SQL | 2021-11-29 | 2021-12-01 |  | 100%
13.4 | Pull all Historical Data Vintages |  |  | R | 2021-12-08 | 2021-12-09 |  | 100%
14 | Model Modulzation (v0.19) |  |  |  |  | - |  |  | -
14.1 | Finish DB Structure |  |  | SQL | 2021-12-22 | 2021-12-22 |  | 100%
14.2 | Add Historical Data Calculated Variables |  |  | R | 2021-12-22 | 2021-12-25 |  | 100%
14.3 | Split Rate Model |  |  | R | 2021-12-25 | 2021-12-26 |  | 100%
14.4 | Add AMERIBOR, SONIA, BSBY Rates |  |  | R | 2021-12-25 | 2021-12-27 |  | 100%
14.5 | Update FFR/SOFR Forecasts |  |  | R | 2021-12-27 | 2021-12-28 |  | 100%
14.6 | Add Raw Forecast Storage to TimescaleDB |  |  | SQL | 2021-12-27 | 2021-12-28 |  | 100%
14.7 | Update TDNS Forecasts |  |  | R | 2021-12-26 | 2021-12-28 |  | 100%
14.8 | Add AMX Forecasts |  |  | R | 2021-12-28 | 2021-12-29 |  | 100%
14.9 | Add BSBY Forecasts |  |  | R | 2021-12-29 | 2021-12-29 |  | 100%
15 | Modularization & Web Release (v0.20) |  |  |  |  | - |  |  | -
15.1 | Add Inflation Forecasts |  |  | R | 2022-01-02 | 2022-01-03 |  | 100%
15.2 | Add Initial External Forecast Import (SPF, WSJ, CBO) |  |  | R | 2022-01-02 | 2022-01-03 |  | 100%
15.3 | Setup Raw Data SQL Tables |  |  | SQL | 2022-01-02 | 2022-01-03 |  | 100%
15.4 | Setup Individual/Baseline Rate Forecast SQL Tables |  |  | SQL | 2022-01-02 | 2022-01-04 |  | 100%
15.5 | Setup Beta Subdomain Web Backend |  |  | Bash | 2022-01-03 | 2022-01-04 |  | 100%
15.6 | Update EF CSS Styling |  |  | CSS | 2022-01-03 | 2022-01-31 |  | 100%
15.7 | Release Individual/Baseline Rate Forecasts on Website |  |  | JS | 2022-01-05 | 2022-01-31 |  | 100%
15.8 | Add Additional External Forecasts |  |  | R | 2022-01-17 | 2022-02-05 |  | 100%
15.9 | Add Python PDF Parsing Support |  |  | Python | 2022-01-17 | 2022-01-31 |  | 100%
15.10 | Update EF Home Page |  |  | HTML | 2022-01-17 | 2022-02-05 |  | 90%
15.11 | CloudFlare Migration |  |  | Bash | 2022-01-31 | 2022-02-01 |  | 100%
15.12 | Update Nowcasts Model |  |  | R | 2022-02-02 | 2022-02-06 |  | 80%
15.13 | Release GDP/Nowcast Forecasts on Website |  |  | JS | 2022-02-06 | 2022-02-09 |  | 0%
15.14 | Release Sentiment Index on Website |  |  | R | 2022-02-09 | 2022-02-10 |  | 0%
15.15 | Final Styling Fixes |  |  | CSS | 2022-02-09 | 2022-02-12 |  | 0%
15.16 | Public Release |  |  | HTML | 2022-02-13 | 2022-02-13 |  | 0%
16 | TBD (v0.21) |  |  |  |  | - |  |  | -
16.1 | Develop Rate Composite Model - Optimal Model Stacking (MRF) |  |  | R | TBD |  |  | 0%
16.2 | Release Rate Vintage Comparison |  |  | JS | TBD |  |  | 0%
16.3 | Release Rate Composites on Website |  |  | JS | TBD |  |  | 0%
16.4 | Rebuild Asset Contagion Index |  |  | R | TBD |  |  | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.